## Slide 1
Biju Pucca Ghar Yojana- PMAY (Rural Housing)
PANCHAYATI RAJ & DRINKING WATER
DEPARTMENT
GOVERNMENT OF ODISHA
DATE:- 28.10.2017

## Slide 2
Houses completed since FY 2014-15
Sl. No. | FY | Schemes |  | 
 |  | PMAY-G & IAY | BPGY, BPGY(M) & NSPGY | Total
1 | 2014-15 | 320895 | 31,526 | 3,52,421
2 | 2015-16 | 502092 | 114726 | 6,16,818
3 | 2016-17 | 117967 | 46016 | 1,63,983
4 | 2017-18 | 143513 | 34709 | 1,78,222
Total |  | 10,84,467 | 2,26,977 | 13,11,444

## Slide 3
Progress during FY 2017-18
Biju Pucca Ghar Yojana | 26971
Biju Pucca Ghar (Mining) | 6472
Nirman Shramik Pucca Ghar Yojana | 1266
Indira Awaas Yojana | 21745
PMAY - G | 121768
Total | 178222
Per day house completion :- 853

## Slide 4
Rank | District | Target |  |  | Achievement |  |  | Total |  | 
 |  | PMAY-G | IAY | BPGY, Mining & NSPGY | PMAY-G | IAY | BPGY, Mining & NSPGY | Tar. | Ach. | %age
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | BHADRAK | 29446 | 5378 | 4467 | 3193 | 238 | 934 | 39291 | 4365 | 11.1
2 | BARGARH | 37784 | 6199 | 5123 | 3158 | 1422 | 1366 | 49106 | 5946 | 12.1
3 | SONEPUR | 17414 | 1730 | 1933 | 2006 | 121 | 427 | 21077 | 2554 | 12.1
4 | KENDUJHAR | 40037 | 6908 | 18094 | 3642 | 1413 | 3086 | 65039 | 8141 | 12.5
5 | KALAHANDI | 33635 | 4140 | 3262 | 3296 | 1050 | 852 | 41037 | 5198 | 12.7
6 | NUAPADA | 18229 | 3214 | 2202 | 1864 | 768 | 451 | 23645 | 3083 | 13.0
7 | MALKANGIRI | 12193 | 3192 | 903 | 1381 | 493 | 287 | 16288 | 2161 | 13.3
8 | KENDRAPARA | 22598 | 4562 | 4920 | 2784 | 886 | 662 | 32080 | 4332 | 13.5
9 | BOUDH | 15021 | 1003 | 2116 | 2008 | 81 | 402 | 18140 | 2491 | 13.7
10 | DHENKANAL | 23113 | 2752 | 3568 | 3210 | 318 | 939 | 29433 | 4467 | 15.2
11 | GAJAPATI | 10453 | 2928 | 902 | 1219 | 806 | 213 | 14283 | 2238 | 15.7
12 | RAYAGADA | 15865 | 1992 | 1067 | 2335 | 355 | 296 | 18924 | 2986 | 15.8
13 | ANGUL | 19771 | 2895 | 4736 | 2301 | 941 | 1252 | 27402 | 4494 | 16.4
14 | JAGATSINGHAPUR | 9020 | 1147 | 2013 | 1282 | 328 | 395 | 12180 | 2005 | 16.5
15 | JAJPUR | 28571 | 4408 | 5840 | 4381 | 857 | 1282 | 38819 | 6520 | 16.8
Total |  | 736257 | 105413 | 130041 | 121768 | 21745 | 34709 | 971711 | 178222 | 18.3
Progress during FY 2017-18

## Slide 5
Rank | District | Target |  |  | Achievement |  |  | Total |  | 
 |  | PMAY-G | IAY | BPGY, Mining & NSPGY | PMAY-G | IAY | BPGY, Mining & NSPGY | Tar. | Ach. | %age
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
16 | NABARANGAPUR | 32490 | 3292 | 3029 | 4341 | 1493 | 722 | 38811 | 6556 | 16.9
17 | KORAPUT | 21471 | 3126 | 4779 | 4016 | 128 | 1039 | 29376 | 5183 | 17.6
18 | NAYAGARH | 13715 | 2073 | 4124 | 2515 | 155 | 893 | 19912 | 3563 | 17.9
19 | DEOGARH | 6748 | 656 | 762 | 1089 | 164 | 239 | 8166 | 1492 | 18.3
20 | BALESHWAR | 35092 | 6640 | 6566 | 6235 | 751 | 1956 | 48298 | 8942 | 18.5
21 | KANDHAMAL | 14248 | 3437 | 1634 | 2480 | 717 | 457 | 19319 | 3654 | 18.9
22 | PURI | 21516 | 5670 | 4631 | 2085 | 2369 | 1581 | 31817 | 6035 | 19.0
23 | KHORDHA | 13329 | 2763 | 3435 | 2524 | 414 | 878 | 19527 | 3816 | 19.5
24 | MAYURBHANJ | 67170 | 7270 | 10760 | 11876 | 2587 | 3417 | 85200 | 17880 | 21.0
25 | JHARSUGUDA | 8751 | 704 | 986 | 1799 | 223 | 400 | 10441 | 2422 | 23.2
26 | SUNDARGARH | 43191 | 1707 | 11305 | 9511 | 60 | 4039 | 56203 | 13610 | 24.2
27 | BOLANGIR | 48651 | 4615 | 4122 | 11474 | 760 | 1757 | 57388 | 13991 | 24.4
28 | CUTTACK | 28959 | 4283 | 5739 | 6844 | 1019 | 1829 | 38981 | 9692 | 24.9
29 | GANJAM | 25502 | 5645 | 4810 | 7321 | 746 | 1430 | 35957 | 9497 | 26.4
30 | SAMBALPUR | 22274 | 1084 | 2213 | 9598 | 82 | 1228 | 25571 | 10908 | 42.7
Total |  | 736257 | 105413 | 130041 | 121768 | 21745 | 34709 | 971711 | 178222 | 18.3
Progress during FY 2017-18

## Slide 6
Completion against 6 Lakh Target
Sl. No. | District | Target | Completed | Daily Average |  | 
 |  |  |  | Required | Current | % (w.r.t required)
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | BHADRAK | 26382 | 4365 | 141 | 21 | 15
2 | SONEPUR | 13575 | 2554 | 71 | 12 | 17
3 | KENDUJHAR | 43457 | 8141 | 226 | 39 | 17
4 | BARGARH | 30939 | 5946 | 160 | 28 | 18
5 | MALKANGIRI | 10555 | 2161 | 54 | 10 | 19
6 | KENDRAPARA | 21512 | 4332 | 110 | 21 | 19
7 | BOUDH | 11982 | 2491 | 61 | 12 | 20
8 | NUAPADA | 14862 | 3083 | 76 | 15 | 20
9 | KALAHANDI | 24724 | 5198 | 125 | 25 | 20
10 | JAGATSINGHAPUR | 9166 | 2005 | 46 | 10 | 22
11 | DHENKANAL | 18435 | 4467 | 90 | 21 | 23
12 | KHORDHA | 15567 | 3816 | 75 | 18 | 24
13 | RAYAGADA | 11497 | 2986 | 55 | 14 | 25
14 | ANGUL | 17773 | 4494 | 85 | 22 | 26
15 | NAYAGARH | 13647 | 3563 | 65 | 17 | 26
Odisha |  | 608203 | 178222 | 2756 | 853 | 31

## Slide 7
Completion against 6 Lakh Target
Sl. No. | District | Target | Completed | Daily Average |  | 
 |  |  |  | Required | Current | % (w.r.t required)
1 | 2 | 3 | 4 | 5 | 6 | 7
16 | JAJPUR | 24144 | 6520 | 113 | 31 | 27
17 | DEOGARH | 5446 | 1492 | 25 | 7 | 28
18 | KORAPUT | 19129 | 5183 | 89 | 25 | 28
19 | BALESHWAR | 31691 | 8942 | 146 | 43 | 29
20 | GAJAPATI | 8075 | 2238 | 37 | 11 | 30
21 | NABARANGAPUR | 22483 | 6556 | 102 | 31 | 30
22 | PURI | 19552 | 6035 | 87 | 29 | 33
23 | KANDHAMAL | 10834 | 3654 | 46 | 17 | 37
24 | CUTTACK | 26547 | 9692 | 108 | 46 | 43
25 | MAYURBHANJ | 48146 | 17880 | 194 | 86 | 44
26 | BOLANGIR | 34649 | 13991 | 132 | 67 | 51
27 | JHARSUGUDA | 6029 | 2422 | 23 | 12 | 52
28 | GANJAM | 22739 | 9497 | 85 | 45 | 53
29 | SUNDARGARH | 30688 | 13610 | 109 | 65 | 60
30 | SAMBALPUR | 13978 | 10908 | 20 | 52 | 260
Odisha |  | 608203 | 178222 | 2756 | 853 | 31

## Slide 8
Critical Issues
  Hon’ble Chief Minister has set a target of completion of 6 lakh houses during the FY 2017-18. To achieve this benchmark, the present per day house completion, which is 853 needs to be speedily ramped up.
  As on date, 7.93 lakh houses are incomplete out of which 3.37 lakh belong to the FY 2016-17. Completion of these houses, which are low hanging fruits, should be focused.
  During the FY 2017-18, 3.54 lakh houses are allotted to Districts (PMAY(G) – 3.40 Lakh , BPGY- 0.12 Lakh , NSPGY- 0.02 Lakh). All the eligible beneficiaries need to be issued with Work Order and released with 1st instalment immediately. Selection of beneficiaries will be village wise instead of GP-wise.
  All the beneficiaries should be paid labour component (wages of 90/95 days) out of MGNREGS and mapped with Mason Training which will boost pace of completion.

## Slide 9
Critical Issues
  All the new beneficiaries should be issued with Work Order for IHHL along with housing Work Order.
  Exemplary punishment for any occurrence of unethical practises should be awarded.
  Monitoring should be strengthened leveraging technology. RH Portal and Mobile App developed by State should be utilized as tools for better monitoring.
  House site should be provided to those eligible beneficiaries, who do not have recorded land so that landless can be covered under the scheme.