## Slide 1: ST&SC DEVELOPMENT DEPARTMENT
COLLECTORS CONFERENCE
28.10.2017.

## Slide 2: SNAPSHOT OF HOSTELS CONSTRUCTED BY STATE GOVT
The ST&SC Development Department has sanctioned 7047 numbers of S.T. hostels till 2017-18.
From the FY 2009-10 till FY 2016-17 a total of 4065 hostels have been sanctioned.
During the year 2016-17, 560 numbers of hostels have been sanctioned under different Schemes, as detailed below.
Out of these 3275 hostels have been completed leaving a balance of 790 hostels. (230 Old Hostels yet to be completed)
Similarly, 532 hostels had been sanctioned for S.C. category out of which 492 buildings have been completed leaving a balance of 40 hostels.
251 | ANWESHA Hostels
303 | Odisha Adarsha Vidyalaya Hostels
6 | Akankhya Hostels

## Slide 3: INCOMPLETE HOSTELS 2009-10 & 2011-12
Status of Incomplete Hostels 2009-10 |  |  | 
Sl No. | Name of the District | Nos. of Incomplete Hostels | Status
1 | Gajapati | 2 | 2 plinth
2 | Malkangiri | 1 | FL-1
3 | Phulbani | 1 | 1/ FFRL
4 | Boudh | 1 | 1- LL
5 | Nuapada | 2 | 1-NS,1-GFRC
 | Total | 7 | 
Status of Incomplete Hostels 2011-12 |  |  | 
Sl No. | Name of the District | Nos. of Incomplete Hostels | Status
1 | Boudh | 1 | 1/ Plinth level
2 | Deogarh | 1 | 1/ FL
3 | Gajpati | 1 | 1/ RL
4 | Kandhamal | 2 | 1/ FFRL, 1-FFLL
5 | Kendrapara | 2 | 1/FL, 1/FS
6 | Malkangiri | 1 | 1/ FFRL
7 | Nuapada | 2 | 2/ RC
8 | Sundergarh | 2 | 2-RC
 | Total | 12 | 

## Slide 4
Status of Incomplete Hostels 2013-14 |  |  | 
Sl. No. | Name of the District | Nos. of Incomplete Hostels | Status
1 | Balasore | 1 | 1/ RC
2 | Bargarh | 7 | 5/ RC, 2/ LL
3 | Bhadrak | 9 | 5- RC,1-RL, 1- LL, 1- PL,1- FL
4 | Bolangir | 5 | 2- FFRL, 1- GFLL,2- FL
5 | Boudh | 11 | FFRL-2, FFLL-2, GFRL-2, GFLL-2, GFLL-2, PL-1
6 | Cuttack | 8 | PL-3, GFRC-2, FL-3
7 | Deogarh | 1 | GRC-1
8 | Jagatsinghpur | 6 | 1-FFRC, 2-GFRC, 1-FL, 1-PL, 1-WO
9 | Jajpur | 3 | FL-3
10 | Jharsuguda | 6 | GRC-2, GRLL-2, FFLL-2
11 | Kalahandi | 1 | FFRC-1
12 | Kandhamal | 2 | FFRL-2
13 | Kendrapara | 7 | Tender Finalised -2, T.S-5
14 | Keonjhar | 1 | FFRC-1
15 | Khordha | 4 | FFRC-2, RL-1,PL-1
16 | Malkangiri | 2 | FFFC-2
17 | Mayurbhanj | 3 | LL-1 , RL-2
18 | Nuapara | 15 | FFRL-5, GFRC-8, GFPL-1, TF-1
19 | Nayagarh | 3 | LL-2, PL-1
20 | Puri | 1 | FFRL-1
21 | Subarnapur | 3 | PL-2, RL-1,
 | Total | 99 | 

## Slide 5
Status of Incomplete Hostels 2015-16 |  |  | 
Sl. No. | Name of the District | Nos. of Incomplete Hostels | Status
1 | Gajapati | 6 | FFRC-5, GFRC-1
2 | Kalahandi | 2 | FFRC-2
3 | Keonjhar | 2 | FL-2
4 | Koraput | 10 | GFRC-2, FS-2, FFRC-2, PL-4
5 | Malkangiri | 4 | LL-2, PL-2
6 | Mayurbhanj | 1 | GFRC-1
7 | Nuapara | 1 | FL-1
8 | Nawarangpur | 11 | FW-7, FFRC-4
9 | Rayagada | 2 | FS-2
10 | Subarnapur | 2 | FL-1, TC-1
11 | Sundergarh | 7 | FW-3, GFRC-3. FFRC-1
12 | Kandhamal | 4 | FW-2, PL-2
 | Total | 52 | 

## Slide 6: STATUS OF ADARSH VIDYALAY HOSTELS
130 Girls and 173 Boys hostels sanctioned during 2016-17.
As per ST SC Dept. the estimated cost for a 100 seated hostel is Rs. 75 lakhs
Similarly for an additional 50 seated hostel for Girls the estimated cost has been pegged at Rs 37.50 lakhs
RD Dept. was requested to furnish the detail estimates. RD Dept. has submitted an estimate of Rs. 235 lakhs for 150 seated and Rs. 70 lakhs For 50 seated hostels.
This is almost 100 % higher than the estimate prepared by ST SC Dept.
State & CPSUs executing similar projects of this Dept. have been requested to indicate their estimated cost.
It is likely that they may do the work at much lower than the estimate submitted by RD Dept.
Once the CPSUs agree to execute within the estimated cost, the work will be executed through them.