## Slide 1
MEGA LIFT PROJECTS
Collectors’ Conference
28.10.2017
GOVERNMENT OF ODISHA
DEPARTMENT OF WATER RESOURCES

## Slide 2
Over View on Megalift Projects
174 nos. of Megalift schemes were identified and grouped into 15 Clusters as per Pre -Feasibility Study done during 2011-12.
Subsequently additional 24 nos. of schemes including One Cluster with 8 schemes in Malkangiri district, 01 scheme in Upper Indravati lift project & 02 schemes in Rengali Right Irrigation Project have been added as per detailed Engineering and field survey and included in different clusters totalling 198 schemes across Odisha.
Out of above , 13 Clusters having 169 schemes under Megalift irrigation Project and one scheme in Upper Indravati Lift Project altogether 170 nos. Schemes with total ayacut area of 2,32,858 Ha. have been taken up at an estimated cost of Rs. 6526.65 Cr .
Tender for 28 Projects to be invited shortly ( Irr. Benefit- 0.41 lakh ha, Cost-Rs.1234.31 Cr.)

## Slide 3: COMMISSIONNING PROGRAMME OF Mega Lift Schemes During FY 2017-18
Sl. No. | District | Name of Scheme | Ayacut Area (Ha.) | Month | Cluster
1 | Baragarh | Jamutpali | 1200 | Nov’17 | III
2 |  | Chikhili | 2000 | Feb’18 | III
3 |  | Jampali | 1320 | Feb’18 | III
4 |  | Tamdei | 1400 | Feb’18 | III
5 | Bolangir | Gurujibhata | 2000 | Oct’17 | XIV
6 |  | Dunguripali | 1000 | Oct’17 | XIV
7 |  | Bhuskimal | 1200 | Oct’17 | XIV
8 |  | Tandigaon | 2000 | Oct’17 | XV
9 |  | Tentulikhunti | 1500 | Oct’17 | XV
10 |  | Mahajanpara | 800 | Oct’17 | XV
11 |  | Sasanpali | 1500 | Oct’17 | XV
12 |  | Siskela | 900 | Nov’17 | XIV
13 |  | Brahmnipal | 2000 | Nov’17 | XV
14 | Boudh | Tambasina | 1500 | Oct’17 | XV
15 |  | Kantamal | 1500 | Oct’17 | XV
16 |  | Tikarpada | 2000 | Oct’17 | XV
17 |  | Rekdol | 2000 | Nov’17 | XV
18 | Cuttack | Chakragarh -II | 2000 | Mar’18 | VI
19 | Deogarh | Masinta | 1650 | Mar’18 | VIII
20 | Gajapati | Bothava | 1102 | Jan’18 | I
21 |  | Sara | 739 | Jan’18 | I
22 |  | Kidigaon-I | 1545 | Feb’18 | I
23 |  | Kidigaon-II | 1301 | Mar’18 | I

## Slide 4: COMMISSIONNING PROGRAMME OF Mega Lift Schemes During FY 2017-18
Sl. No. | District | Name of Scheme | Ayacut Area (Ha.) | Month | Cluster
24 | Jharsuguda | Kudabaga | 500 | Nov’17 | III
25 |  | Sodamal | 800 | Dec’17 | III
26 |  | Katikula | 800 | Feb’18 | III
27 |  | Samsingha | 1000 | Feb’18 | III
28 |  | Renkuli | 500 | Mar’18 | III
29 | Kalahandi | Palam | 2000 | Oct’17 | XIV
30 |  | Hatikhoja | 2000 | Oct’17 | XIV
31 |  | Chandpur | 500 | Oct’17 | II
32 |  | Chatabandugra | 900 | Oct’17 | II
33 |  | Tundla - I | 500 | Nov’17 | XIV
34 |  | Tundla - II | 600 | Nov’17 | XIV
35 | Kendrapara | Deulatara | 1200 | Mar’18 | XI
36 | Nabrangpur | Dahibhata | 999 | Mar’18 | II
37 |  | Nuagam | 677 | Mar’18 | II
38 | Rayagada | Bhimpur | 756 | Feb’18 | I
39 |  | Gadiakhal-II | 787 | Feb’18 | I
40 |  | Gadiakhal-I | 825 | Mar’18 | I
41 |  | Nuagan | 600 | Mar’18 | I
42 | Sambalpur | Jankdihi | 1300 | Oct’17 | III
43 |  | Sairha | 2000 | Nov’17 | III
44 |  | Budlapali | 1500 | Dec’17 | III
45 |  | Chandnimal | 1500 | Feb’18 | III
46 |  | Manapali | 1500 | Feb’18 | III
47 |  | Rampila-I | 1500 | Mar’18 | III
48 |  | Rampila-II | 1700 | Mar’18 | III
49 |  | Nuagan | 2000 | Mar’18 | III

## Slide 5
COMMISSIONNING PROGRAMME OF Mega Lift Schemes During FY 2017-18
Sl. No. | Month | No. of Schemes | Irr. Potential to be created in (Ha.)
1 | October, 2017 | 19 | 26400
2 | November, 2017 | 8 | 9700
3 | December, 2017 | 2 | 2300
4 | January, 2018 | 2 | 1841
5 | February, 2018 | 10 | 12608
6 | March, 2018 | 14 | 17052
 | Total | 55 | 69901
ABSTRACT
Sl. No. | District | Name of Scheme | Ayacut Area (Ha.) | Month | Cluster
50 | Subarnapur | Amdahan | 800 | Oct’17 | XV
51 |  | Ainapali | 1500 | Oct’17 | XV
52 |  | Gunjimunda | 800 | Oct’17 | XV
53 |  | Pandkimal | 1600 | Oct’17 | XV
54 | Sundergarh | Satakuta | 600 | Mar’18 | VIII
55 |  | Biritola | 1500 | Mar’18 | VIII
 |  | 55 Schemes | 69901 |  | 

## Slide 6
DISTRICTWISE ISSUES OF MEGALIFT PROJECTS
In Jamutpali scheme, Villagers of Barmunda of Gaisilat block, Dist: BARGARH are not allowing erection of 40 nos.poles.
In Agalpur & Bharsuja scheme of Agalpur block, Dist: BALANGIR, the available voltage is very less due to which continuous operation is not possible. It will improve only after isolation of Gaisalat Supply from the proposed Pathampur 133 KV sub-station.
In 10 nos. schemes under cluster XV, Dist: BALANGIR, BOUDH & SUBARNAPUR, Land Owners are not allowing erection of 40 poles from Tusura Grid to MSDSS-8, 9. Collector, Balangir to Intervene.
In Siskela Scheme, Saintala block under Cluster XIV, Dist: BALANGIR, Land owners are demanding higher compensation. Tahasildar Saintala to intervene regarding partition deed among the land owners.
In Palam scheme, Narla block under Cluster XIV, Dist: KALAHANDI, Villagers of Sallebhatta & Khairamala are not allowing laying of 140 m. Rising Main pipeline. Collector, Kalahandi to Intervene.

## Slide 7
DISTRICTWISE ISSUES OF MEGALIFT PROJECTS
In Mahupadar Scheme, Mathili Block under Cluster II, Dist: MALKANGIRI, Due to extremist activities, work could not be started. District Administration to intervene.
In Gobardhanpur scheme, Mahakalpada Block under Cluster XI, Dist: KENDRAPADA, Local miscreants are often creating hindrances in work. Collector, Kendrapada to intervene.
In Baliput Scheme, Narsinghpur Block under Cluster VI, Dist: CUTTACK Clearance for Delivery chamber construction in satkosia reserve forest area is pending with DFO, Angul.
16 nos. of Land alienation Proposals, Dist: CUTTACK is pending with Revenue Authority at different stages. District Administration to intervene.
Similarly, Land Alienation proposals of different districts are pending at various stages of District Administration.

## Slide 8
THANK YOU