## Slide 1
Odisha Lift Irrigation Corporation
<number>
Collectors Conference
28.10.2017

## Slide 2: Lift Irrigation(Issues)
Collection of beneficiary share (Old scheme).
Regular review and coordination between DISCOMS and OLIC field functionaries to sort out energization related issues.
Repair and revival of Partially defunct Community lift irrigation projects in Drought affected blocks.
Funding of Defunct projects under District Mineral Fund.

## Slide 3: 1. Collection of beneficiary share (Old scheme)
Beneficiary contribution is pending in 10066 projects due to which Project could not be completed.
Districts like Boudh(1539),Subarnapur(1384),Sambalpur(1266),Kalahandi(668) and Khurda(660) have highest beneficiary share pending.
District collectors to coordinate and ensure beneficiary contribution at the earliest.

## Slide 4: Deep bore well 2010-11 to 2014-15 (Off line) beneficiary share not received
Sl. No. | Name of District | No. of application received | No of Eligible Application | Eligible Application for drilling attempted | No. beneficiary share received | No. of YDD success DBWs | Nos of DBWs. energized | % of Achievement So-Far | No. for which beneficiary share not received
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | Boudh | 8261 | 4898 | 4898 | 2303 | 3842 | 2303 | 100 | 1539
2 | Subarnapur | 8388 | 4273 | 4273 | 2517 | 3901 | 2482 | 99 | 1384
3 | Sambalpur | 11764 | 6650 | 6645 | 4205 | 5471 | 4098 | 97 | 1266
4 | Kalahandi | 6655 | 3960 | 3942 | 2427 | 3095 | 2340 | 96 | 668
5 | Khurda | 3081 | 2266 | 2256 | 773 | 1433 | 752 | 97 | 660
6 | Bolangir | 10016 | 6517 | 6507 | 4112 | 4658 | 4075 | 99 | 546
7 | Nayagarh | 3681 | 1990 | 1990 | 1168 | 1712 | 1139 | 98 | 544
8 | Nuapada | 5227 | 4550 | 4540 | 2057 | 2431 | 1986 | 97 | 374
9 | Jharsuguda | 3010 | 2050 | 2024 | 1051 | 1400 | 1051 | 100 | 349

## Slide 5
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
10 | Bargarh | 15325 | 5889 | 5889 | 6790 | 7127 | 6770 | 100 | 337
11 | Mayurbhanj (Karanjia) | 5225 | 2950 | 2935 | 2138 | 2430 | 2042 | 96 | 292
12 | Deogarh | 3670 | 2989 | 2989 | 1457 | 1707 | 1456 | 100 | 250
13 | Malkanagir | 3249 | 2181 | 2181 | 1262 | 1511 | 1237 | 98 | 249
14 | Nabrangpur | 5530 | 3187 | 3187 | 2341 | 2572 | 2280 | 97 | 231
15 | Anugul | 4427 | 1722 | 1722 | 1867 | 2059 | 1851 | 99 | 192
16 | Mayurbhanj (Baripada) | 3318 | 2099 | 2091 | 1358 | 1543 | 1350 | 99 | 185
17 | Balasore | 2387 | 960 | 951 | 940 | 1110 | 858 | 91 | 170
18 | Jajpur | 2198 | 1065 | 1036 | 863 | 1022 | 837 | 97 | 159
19 | Sundergarh (Sundergarh) | 3715 | 2696 | 2696 | 1569 | 1725 | 1522 | 97 | 156
STATUS OF BORE WELL-2010-11 to 2014-15 (Off line) beneficiary share
not received

## Slide 6
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
20 | Raygada | 2329 | 1931 | 1931 | 967 | 1083 | 961 | 99 | 116
21 | Kandhamal | 1621 | 2003 | 1947 | 575 | 674 | 570 | 99 | 99
22 | Sundergarh (Rourkela) | 6193 | 4340 | 4340 | 2784 | 2880 | 2740 | 98 | 96
23 | Keonjhar | 2873 | 3513 | 3513 | 1183 | 1256 | 1169 | 99 | 73
24 | Koraput | 1277 | 1014 | 1014 | 527 | 594 | 527 | 100 | 67
25 | Ganjam | 1019 | 804 | 794 | 445 | 474 | 440 | 99 | 29
26 | Dhenkanal | 1793 | 911 | 911 | 817 | 834 | 800 | 98 | 17
27 | Gajapati | 314 | 275 | 265 | 136 | 146 | 103 | 76 | 10
28 | Cuttack | 903 | 725 | 725 | 412 | 420 | 411 | 100 | 8
TOTAL |  | 127451 | 78409 | 78192 | 49044 | 59110 | 48150 | 98 | 10066
STATUS OF BORE WELL-2010-11 to 2014-15 (Off line) beneficiary share
not received

## Slide 7: 2. Coordination between DISCOMS and OLIC field functionaries
Regular review at collectors level-to reduce issues related to Energization and charging.
Issues like delay in submission of Estimate, Inspection and charging may be sorted out by collectors active intervention.
A total of 758 projects pending for Charging alone.
Districts like Bargarh(439),Nuapada(84),Anugul(77) have projects not completed due to Charging related issues.

## Slide 8
Summery of Physical achievement of OLIC
2015-16 to 2016-17 On-Line for energisation (in Nos)
No. of Appln Recd. With FD | Eligible Application after Pre-Feasibility | Drilling Attempted | Successful DBWs after YDD & to be taken for Energisation | DBWs Energised and Handed Over | % of Achievement | Balance to be Energised
1 | 2 | 3 | 4 | 7 | 8 | 9
30,390* | 25,969 | 24,850 | 18,806 | 5,541 | 30 | 13,265
Nos. Drilling to be taken up in two Packages(1-Non-Responsive & one Sub-Judice) - 1119 Nos
Electrification works in progress and to be completed by 15th Nov - 4572 Nos
Job Order for Energisation issued to Service Provider and to be completed by - 8,693 Nos
Jan’2018
* Position of Application with FD up to-March’2017

## Slide 9: STATUS OF On-Line BORE WELL 2015-16 to 2016-17 for Energisation
Sl. No. | Name of the District | Appln. With beneficiary share received | Eligible Application after feasibility | No. for which drilling attempted | No. of DBWs after YDD success | Nos. energised | % of Achievment | Balance to be Energised
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | Bargarh | 7869 | 7776 | 7824 | 6891 | 1031 | 15 | 5860
2 | Bolangir | 3293 | 2875 | 3413 | 2374 | 610 | 26 | 1764
3 | Sundergarh | 2750 | 2620 | 1871 | 1236 | 383 | 31 | 853
4 | Ganjam | 1827 | 1273 | 1149 | 879 | 68 | 8 | 811
5 | Anugul | 1136 | 1046 | 926 | 700 | 197 | 28 | 503
6 | Keonjhar | 1390 | 1178 | 662 | 374 | 13 | 3 | 361
7 | Jharsuguda | 619 | 420 | 893 | 642 | 292 | 45 | 350
8 | Nuapada | 1476 | 948 | 1120 | 744 | 402 | 54 | 342
9 | Koraput | 1298 | 1049 | 912 | 692 | 373 | 54 | 319

## Slide 10
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
10 | Nabrangpur | 1296 | 1239 | 1025 | 843 | 527 | 63 | 316
11 | Sambalpur | 906 | 756 | 1077 | 679 | 375 | 55 | 304
12 | Kalahandi | 955 | 602 | 768 | 503 | 275 | 55 | 228
13 | Dhenkanal | 532 | 416 | 458 | 370 | 199 | 54 | 171
14 | Jajpur | 320 | 305 | 255 | 210 | 41 | 20 | 169
15 | Raygada | 1150 | 962 | 478 | 306 | 138 | 45 | 168
16 | Deogarh | 342 | 14 | 362 | 258 | 106 | 41 | 152
17 | Khurda | 324 | 267 | 279 | 225 | 88 | 39 | 137
18 | Mayurbhanj | 984 | 542 | 419 | 235 | 129 | 55 | 106
19 | Gajapati | 251 | 224 | 93 | 82 | 0 | 0 | 82
STATUS OF On-Line BORE WELL 2015-16 to 2016-17 for Energisation

## Slide 11
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
20 | Cuttack | 258 | 199 | 113 | 93 | 20 | 22 | 73
21 | Nayagarh | 264 | 205 | 153 | 75 | 6 | 8 | 69
22 | Malkanagir | 330 | 325 | 299 | 237 | 173 | 73 | 64
23 | Balasore | 113 | 105 | 69 | 57 | 3 | 5 | 54
24 | Subarnapur | 280 | 267 | 225 | 101 | 92 | 91 | 9
25 | Boudh | 58 | 36 | 7 | 0 | 0 | 0 | 0
26 | Kandhamal | 369 | 320 | 0 | 0 | 0 | 0 | 0
 | Total | 30390 | 25969 | 24850 | 18806 | 5541 | 29 | 13265
STATUS OF On-Line BORE WELL 2015-16 to 2016-17 for Energisation

## Slide 12
<number>
Sl. No. | Name of the District | Total
1 | 2 | 3
1 | Bargarh | 439
2 | Nuapada | 84
3 | Anugul | 77
4 | Balangir | 50
5 | Sundergarh (Sundargarh) | 29
6 | Malkanagiri | 23
7 | Dhenkanal | 19
8 | Mayurbhanj (Karanjia) | 13
9 | Sambalpur | 10
10 | Gajapati | 10
11 | Nayagarh | 4
Total |  | 758
No. of Bore Wells where electrification is completed and awaiting charging alone as on 26.10.2017

## Slide 13: 3. Repair and revival of Partially defunct Community lift irrigation projects in Drought affected blocks
Detailed guidelines issued vide letter no 23004 Dt 16.10.2015
Committee under the chairmanship of Collector shall identify LIP for immediate repair.
For immediate repair, 924 nos. LIPs are identified with an approximate cost of Rs.6.02 cr.

## Slide 14
<number>
Programme for Short term drought mitigation plan-OLIC
Sl. No | Name of District | No. of Blocks | Nos. of Projects involved |  |  |  | Approx. Estimated cost (Rs. In Lakhs) | Area to be benefitted ( in Hect)
 |  |  | OLIC | DISTCOS | OLIC & DISTCOS | Total |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
1 | Angul | 8 | 129 |  |  | 129 | 56.15 | 1200
2 | Balasore | 3 | 21 |  |  | 21 | 7.06 | 315
3 | Bargarh | 10 | 26 | 3 | 2 | 31 | 31.05 | 400
4 | Bhadrak | 5 | 62 |  | 13 | 75 | 95.23 | 710
5 | Bolagnir | 10 | 41 | 10 | 18 | 69 | 59.85 | 759
6 | Boudh | 2 | 22 | 2 |  | 24 | 54.57 | 480
7 | Cuttack | 14 | 136 | 17 | 10 | 163 | 28.95 | 2400
8 | Dhenkanal | 6 | 101 |  | 12 | 113 | 80.01 | 1300

## Slide 15
<number>
Sl. No | Name of District | No. of Blocks | Nos. of Projects involved |  |  |  | Approx. Estimated cost (Rs. In Lakhs) | Area to be benefitted ( in Hect)
 |  |  | OLIC | DISTCOS | OLIC & DISTCOS | Total |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
9 | Deogarh | 1 |  |  | 1 | 1 | 5.68 | 16
10 | Jagatsingpur | 8 | 51 |  | 10 | 61 | 34.14 | 900
11 | Jajpur | 4 | 70 |  | 3 | 73 | 36.57 | 584
12 | Jharsuguda | 2 | 30 |  | 4 | 34 | 16.7 | 340
13 | Kandhamal | 5 | 25 |  | 2 | 27 | 9.66 | 270
14 | Keonjhar | 8 | 29 | 2 |  | 31 | 9.01 | 310
15 | Mayurbhanj | 1 | 6 |  | 9 | 15 | 19.81 | 264
16 | Nuapada | 4 | 46 |  | 11 | 57 | 57.42 | 600
Total |  | 91 | 795 | 34 | 95 | 924 | 601.86 | 10848

## Slide 16: 4.Funding of Defunct projects under District Mineral Fund
Collectors may examine the possibility of funding under District Mineral Fund.
Complete list of defunct LIP is available with respective Executive engineers.

## Slide 17
Thank You
<number>